A.	NC3A - 11890- generators

½ payment sent to KFM on Wed, 12 March.

NEXT STEP:  order for expediting shipment/more equip. – RG and JT spoke with LM on 3/22:  LM working on getting expedited paperwork, he said we should be getting something possibly this week; additional equipment has been requested by NC3A (plugs/cords) that KFM is supplying.

B.	NC3A – 11773 – Dan Fancher (JDSK)

LG sent email to customer on 2/14 asking if 90d extension will be exercised (contract is 90d base + 90d option). As of end Feb, Fancher has 19d remaining on base 90d period. Most likely that Fancher’s next invoice for March will consume these 19d.

NEXT STEP:  Per LM email on 3/21, LM will meet with Jim Wager to clarify.

C.	NC3A – Ed Taylor – contract #?

LM provided Taylor’s signed Consult. Agreement (CA), saying he starts 3/27, but LG and JT have no info/paperwork (except this CA).

NEXT STEP:  LM please provide contract, Taylor’s rate, ManTech rate, etc. so PO can be issued.

D.	NC3A – SPIEP 1435 – ISI/Rau overpayment issue

Yannis from ISI responded on 3/13 saying he will get ManTech actual months Rau worked in hostile zone and he acknowledges overpayment of 29,920 EUR.

NEXT STEP:   Still have not rec’d notification of months Rau in hostile zone; once confirmed, JT can reconcile NC3A billing (at NC3A’s request, insurance was billed separately from labor); have we received any money back from ISI?

E.	NACMA - TO23 - Odie Evans – “responsibility allowance”

Previous contract rate was base rate + responsibility allowance of 65 EUR/d for Odie; AMD5 rate for Odie is 869 EUR/d; SHOULD the + 65 EUR/d responsibility allowance still be included each month? So total bill rate to NACMA eff. Feb 2006 is 869 + 65 = 934 EUR/d.

NEXT STEP:  LM to confirm if this additional 65 EUR/d should still be from Feb 2006 onward.; need this confirmed so JT can update figures, notify Lynne, and invoice customer.

F. 	NACMA - TO24 - Al Doman

Need his timesheet for week ending 5 March, so I can invoice NACMA for Feb. I have all other timesheets for month of Feb. Per LM, he will send me Al’s timesheets each month.

NEXT STEP:  LM said he would send to JT; still not rec’d.

G.  	JALLC - 05-46 - updated contract with all names

Rec’d email from Joe Moeder providing update and spreadsheet of staffers; per Joe, we still have to wait for Luca to send us contract listing Hansen, Meehan, Rendina, Stewart, Thordsen. Some staffers do not have POs b/c we do not have the contract with their names/rates/POP updated.

NEXT STEP:  LG to contact/remind Luca when the timing is right.

H.	JALLC – 05-46 - Callum Stewart (KFM) PO and invoice

Rec’d KFM invoice for Stewart, new staffer on JALLC, he worked 6d in Feb. Per RG, invoice cannot be paid until ManTech receives signed contract for Stewart. Also, PO to KFM has not been created b/c of unsigned contract status.

NEXT STEP:  Once we receive updated JALLC contract with Stewart, his PO can be issued and invoice paid.

I. 	JFC HQ Brunssum - 165/05 - Cornett/Teeter

Cornett resigned 3/10; Teeter (employee) replaced Cornett. Still have not received amended contract adding Teeter’s name and POP. The latest document ManTech has states “this requirement is subject to the approval of the MBC 2006 Budget. Upon receipt of approval you will be duly informed by JFC HQ Brunssum.”  We have not been duly informed yet.

NEXT STEP:  LG contacted Capt. Giovannetti 3/22 to request contract. Awaiting contract for Teeter.

## J.	SHAPE – 03-174 - Van Nimmen (contract finished end 2004) – Aubay invoices

Aubay is looking for payment on a few invoices. My records show we are all squared away with them. A bit complicated, JT researching.

NEXT STEP:  JT will research invoicing and provided update.