**Summary – AFGHANISTAN MISSION NETWORK-VTC INSTALLATION AND TRAINING**

**Due: 4/13/2010**

**De*scription of Work***: NATO C3 Agency has requested that ManTech provide a presolicitation proposal for Afghanistan Mission Network-VTC equipment installation and training. Mantech will procure and install POLYCOM equipment at ISAF, Afghanistan. We will also train users at ISAF in use of the equipment.

Type of contract: FFP

Elements:

FP Labor 199,645

POLYCOM Equipment 529,169

FP Travel and Per Diem 24,322

**FFP TOTAL** **753,136**

Estimated Profit: 22%

Estimated Hours: 2,076

Phase1: Polycom Training in Colorado Springs, CO for two ManTech employees (one month)

Phase 2: Pre-Deployment initial configuration of equipment of equipment at SHAPE in Belgium (two weeks)

Phase 3 Implementation and integration support at ISAF, Afghanistan and training of on-site operators (six weeks)

To be awarded under Contract CO 11853 OPL

Sole Source

Risks:

Performance Guarantee (10% of price)

Liquidated Damages Clause

Travel to Afghanistan dependent upon Customer’s schedule. This could increase Per Diem cost in Belgium.

NATO Security clearances required