Portfolio Review:

Women’s Rights Program in Open Society Afghanistan

Introduction

Women have made significant gains over the past 12 years, including significant strides in political life, education, health, and civil society organizing. Despite considerable threats, women turned out in large numbers in 2014 Presidential Elections (36%).  There are significant numbers of women now engaged in public life, from local councils to parliamentary elections to the broadcast media. In urban areas women’s access to justice, health care and education have improved dramatically, though the picture is very different in rural areas, where women continue to be largely excluded from public life.

In recent years we’ve already seen the potential threat posed to these achievements, particularly from the conservative faction in political life. For instance, one of the most tangible achievements of recent years was the passage of the Elimination of Violence Against Women (EVAW) law. However, when recently debated in Parliament, conservative parliamentarians objected to various provisions they declared “un-Islamic,” including access to women’s shelters and the prohibition of child marriage and  domestic violence. Similarly, in 2013 Parliament included a provision in the draft criminal procedure code that would prohibit testimony of relatives in criminal cases, rendering domestic violence prosecutions virtually impossible. The 2013 Afghan election law reduced the women’s quota for provincial council seats from 25% to 20%, though this was unconstitutional, and has been a great boon to female political representation.

A significant concern is the potential threat to women human rights defenders in the years to come, and the lack of a systematic approach to protect women activists: this emerged as a priority issue at a major national gathering of women last year. The Afghan Women’s Network and a few individual CSOs are currently working on a mechanism to address this.

So far, the strength of women’s rights activists, advocates and organizations successfully fought off major challenges.  Looking ahead, women human rights defenders will be greatly tested, with the withdrawal of international troops by the end of 2014, the reduction of INGOs supporting women’s rights, the uncertainties of political transition, the continued or growing power of conservatives in political life and the remaining possibility of peace talks with the Taliban, all of which could negatively impact women’s rights and threaten the achievements of the past 12 years.

Open Society Afghanistan’s Ambitions in this Work

Open Society Afghanistan’s (OSA) has made women’s rights a central platform of its work, in recognition of its importance to the Foundation, and the potential threat to women’s rights in coming years. Our primary ambition in the field is to protect and promote the gains of women that have been made since the fall of the Taliban.

Since its establishment in 2008, OSA has been a leading supporter of Afghan civil society, as a grant maker, and as a neutral venue to promote cohesion and more effective coordination and collaboration among civil society.  Women’s rights work has always been a strong feature of OSA’s grant making and advocacy work, though until the 2014 strategy revision it was a component of the Human Rights portfolio, alongside transitional justice. At the end of 2013 OSA stopped making grants in the field of transitional justice, out of a sense that the political conditions were not conducive to impact. We realized that OSA’s investment will not be as effective in this field as it can be in women’s rights work. However, OSA staff remains committed to their role as a convener and advocate for transitional justice, and has continued to support the Transitional Justice Coordination Group (TJCG) which was initiated by OSA. If opportunities arise in the future OSA remains open to restoring to work in this sector.

In the past OSA’s engagement in the field of women’s rights has been very broad. Our overall ambition was to increase women’s access to their fundamental rights which included improving girls’ access to education, increasing women’s political representation/leadership, improving women’s access to justice, raising public awareness about women’s rights and abuses against women, and protecting the gains made for women in any future peace process. Examples of past grant-making includes: community-level workshops to promote women’s civic engagement; trainings and awareness raising about democratic practice, particularly targeting illiterate women; and strengthening the capacity of women’s groups to develop and implement advocacy strategies to reduce domestic violence. OSA supported a range of grants to improve legal awareness among vulnerable groups and improve their access to justice; this included establishing a Girls’ Rehabilitation centre in a female prison in Kabul with legal aid and skills training. OSA also used media as a tool to improve understanding of women’s rights challenges by supporting media programs promoting women’s rights, including capacity building for female journalists, particularly on women’s rights issues, producing TV advertising, radio dramas and round tables to raise awareness of public on women’s rights. While using media as a tool isn’t an explicit element of our current strategy, we recognize that it is often at the cutting edge of promoting women’s rights and advocating against injustice within the broader population, as well as among opinion and policy makers.

While the ambitions of these individual grants were clear, as a strategy this approach lacked coherence and was quite difficult to come up with tangible impact.

As a result, based on a 2013 assessment of OSA, there are now just two priority areas for its 2014-17 strategy: strengthening moderate interpretations of Islamic law in support of women’s rights; and combatting sexual abuse and harassment.

Women’s Rights from Moderate Islamic Perspective (Concept)

In anticipation of the conservative resurgence or increased contestation of women’s rights on religious grounds, there is a strong need for women’s rights advocates to increase their knowledge of Islam and Islamic law. Women’s rights defenders say they need to be better equipped to defend their rights in a debate that can be dominated by religious interpretations. To meet this need, we will establish a network of religious scholars who will defend and promote women’s rights within Islam, and inform women’s rights defenders. We will further support and develop a body of information on diverse and alternative interpretations of women’s rights under Islam; ensuring broad dissemination of materials and approaches to increase understanding of community religious leaders on women’s social protection, and raise awareness of community decision-makers to encourage them to protect women at risk.

There are some risks in this strategy, including the potential for being co-opted by more extremist elements, and creating an artificial divide between ‘religious’ and ‘secular’ advocacy strategies in a country that is almost entirely Muslim. There is also a risk that ‘instrumentalizing’ Islam as a quick-fix solution can undermine activists who do not feel a sharia framing is necessary to, for instance, raise awareness against violence and other criminal acts.

I have learned that interpretations of Sharia by religious leaders are strongly influenced by cultural values and the social context. To support relatively diverse interpretations of Sharia, OSA will try to introduce Sharia arguments developed in other countries and regions. This can also address some of the cultural gaps that hinder pluralistic views. Diversifying the interpretation of Sharia will also enable both activists and the governmental officials to select the best options of interventions which are in line with the constitution and the international treaties that Afghanistan is a signatory to them.

I am  representing OSA  in a coordination body on Women’s Rights from Islamic perspective, where I  have discovered our approach is significantly different from most of donors and international organization in this field, since OSA tends to empower women and women’s rights activists to strengthen their arguments against extremist religious scholars including support pro-women’s rights religious scholars, whereas other players are mostly working with religious scholars which may increase risk of strengthening arguments of anti-women’s rights religious leaders.

Sexual Harassment (Field)

Sexual harassment is a grave and prevalent problem in the Afghan society, but few women’s rights activists and organizations have taken up this issue. Some women’s rights organizations have shown interest in this field, including emerging youth activists, though there has been a lack of donor intervention on this issue. OSA will fill this gap and work with grassroots organizations, especially with educational institutions, to tackle endemic harassment by building the capacity of young women for self-defence. We will explore regional exchanges to help emerging anti-harassment organizations learn from the development of campaigns in similar environments, including India. We may work with media to generate anti-harassment tools, which have been effective in other countries.

Key Players and Trends in the Women’s Rights Sector

Trends

In general the women’s rights movement in Afghanistan has been the strongest and best organized segment of civil society. They have made significant gains for women and girls, shown great resilience to threats and attacks against women’s rights defenders, and also shown themselves able to respond to crises with collective advocacy and media campaigns. NGOs dominate the field (see lessons learned), but it has been encouraging in the last 2-3 years to see more grass-roots and voluntary efforts returning to the field.

Looking forward it is quite likely that the environment for women’s rights will worsen through transition, given the important role which the international community has played in providing diplomatic and financial support for many of the leading actors. However the women’s rights activists are looking for ways and approaches that how they keep that momentum and protect their gains (e.g. there is strong campaign in progress to encourage women to participate in second round of election and cast their vote). The new President will be Abdullah Abdullah or Ashraf Ghani, both of whom are relatively progressive on women’s rights as individuals, but both of whom have made deals with significant former warlords and conservative factions which could become more influential. Pakistan seems likely to continue supporting the Taliban under either presidency, and the Taliban leadership is increasing its direct attacks on Afghan civilians, including women and girls. The makeup of the new parliament in 2015 will be significant; the last parliamentary elections saw the conservative faction dominating, but also a new crop of young MPs and there is great efforts and preparation going on among civil society to support educated young women and men to be candidate for 2015 parliament.

Major players

The Afghanistan Independent Human Rights Commission (AIHRC) is the leading human rights organization in the country, and is an important advocacy voice for women’s rights. They also have a casework function, with provincial offices in 10 provinces, assisting women victims of human rights abuses. They intend to expand this by developing a cadre of legal aid defence lawyers, who will focus on strategic litigation. The AIHRC is led by one of the most powerful women’s rights defenders in the country, Dr. Sima Samar, with an active Women’s Commissioner, Soraya Sobrang. The challenge for the AIHRC is that their independence is compromised by the Executive control over appointments, which resulted in the removal of two leading Commissioners in 2012-3 (one of whom was replaced by a former Taliban commander).

The Afghan Women’s Network (AWN) is the broadest civil society network on women’s rights. It represents around 84 women’s organizations and 5000 individual members who are committed to support Afghan women across the country. AWN plays an important advocacy role, focused on priorities such as women’s inclusion in peace and security decisions, women’s political participation and social and legal protection of women, much of which is complementary to OSA’s objectives.

Organizations such as Afghan Women’s Skills Development Centre (AWSDC), Women for Afghan Women (WAW), and Humanitarian Assistance for Women of Children of Afghanistan (HAWCA) and the Voice of Afghan Women provide shelters and legal assistance for women who are victims of the domestic violence in Kabul and other provinces. There are also organizations that provide legal aid for women (some of whom are OSA grantees past or present).

Organizations such as the Women and Children Legal Research Foundation (WCLRF) and the Research Institute for Women, Peace and Security (RIWPS) conduct research and advocacy, alongside the AIHRC and AWN, to push the government to implement law and policies that support women’s rights.

The structure of traditional civil society, such as various forms of village and elder councils has existed in Afghanistan for decades. These structures have sometimes been helpful in advocacy efforts to reduce violence against women, nevertheless local councils which were established by extremist traditional elders and religious leaders in some rural areas have undermined women’s rights through informal justice, particularly in the adjudication of family disputes and violence. Some efforts have been made through organizations such as the Empowerment Center for Women to engage in outreach and advocacy with local community and religious leaders.

There are also number of other volunteer structures that are actively supporting women‘s rights at the ground that are adequate such as Young Women for Change which is basically a volunteer group formed in 2011. YWC is made up of dozens of female and male volunteer advocates across Afghanistan, committed to empowering Afghan women through social and political participation. They were able to organize the first ever anti-street-harassment protests in the summer of 2012.

Women’s Political Participation Committee: a coalition movement of women that aims to empower women in their political participation. WPPC have been very active over the past 10 years, including during the EVAW campaign and presidential election.

50% Campaign: This campaign was started during the 2009 Presidential election campaign to express the idea that women are 50% of the population, and are equally victims of war in Afghanistan, but their rights are not considered equally. This group advocates for women’s political and social rights including monitoring of election processes for greater equality and accountability.

Women Are Not a Project: A new social media campaign by women’s rights groups against project based and ‘artificial’ work of some NGOs.

There are also some government structures that are relevant to women’s rights work in Afghanistan. The Ministry of Women’s Affairs (MoWA) is engaged in legal assistance, economic opportunities, education and capacity building for women.  Under the current leadership MOWA hasn’t been very strong, though there are individuals and local offices that play a constructive role. There are gender units in each ministry of various degrees of strength. Commissions have been introduced in all 34 provinces to ensure some implementation of the Elimination of Violence against Women law. Family courts have grown in number and strength, with some playing a progressive role in urban areas.

Some regional networks also exist in South Asia that seek to combine women’s efforts in Afghanistan, Pakistan, India, Nepal and elsewhere to create a more powerful voice, such as the Women Regional Network, South Asians for Human Rights, and the N- Peace Network.

Lastly, a number of international players and donors remain relevant in the field:

- The UN Assistance Mission in Afghanistan (UNAMA): Research and advocacy support on a range of women’s rights issues, including EVAW and traditional conflict resolution mechanisms.

- UN Women: women’s shelters, gender mainstreaming, limited emergency protection funds.

- UNDP: women’s political participation.

- Heinrich Boll Stiftung (HBS): they’ve worked with women parliamentarians on transition, increasing women’s political engagement, and the enforcement and implementation of family law.

- Tawanmandi: A large trust fund for civil society created by European donors that includes grants to women’s organizations primarily for VAW work.

- Women in Transition fund (WIT): launched by USAID in 2012, a $250m fund over 3 years, focused on enhancing the technical and leadership skills of young women.

- Care International: community-based education for girls, also programs for war widows.

- The Asia Foundation: Access to justice for women and women rights in Islam.

- OXFAM GB: Access to justice, VAW, women’s leadership.

- Institute for Inclusive Security (IIS): Supports advocacy on women, peace and security.

Lessons Learned

As previously noted, after a review of OSA’s previous Human Rights portfolio, we decided to change the program into one focused entirely on women’s rights. Within the Human Rights portfolio OSA had included a wide range of challenges, including transitional justice, social inequality for women, youth, war victims, and groups with disability, children and many others. Within the field of transitional justice, while of deep importance to the future of Afghanistan, OSA’s investments had shown limited return, due to adverse political conditions. On the issue of women’s rights particularly, I felt OSA could be more effective by focusing on more specific issues. While OSA had achieved some great successes in its previous women’s rights work (for example, working with community elders to obtain more than 100 signatures in Mazar province on a resolution against child and force marriages), I realized that it had too many objectives, and was spread too thin given the long-term nature of these challenges and the significant investments required.  Similarly I recognized that there are many actors in the field of women’s rights work, often with larger budgets than OSA. However, given the enormity of the challenges in the years to come, and the strength and commitment of OSA to be an influential convener and grant maker, I decided to continue working only in women’s rights, with a narrow focus on unique and innovative areas of investment where our resources could have greater impact.

Another lesson learned was that our emphasis on women claiming their rights overlooked relations between men and women, and that greater inclusion of men in women’s empowerment would increase the chances of sustainable change, especially in the most conservative parts of the country. One way to include men in the push for women’s rights is to reach out to those in traditional and religious leadership positions.

Over the years OSA has supported many grants that focus on trainings and awareness raising around women’s rights, which OSA felt was a necessary first step to improve women’s rights, because without awareness among the target group about their rights positive changes won’t be possible. Consequently OSA - and many other donors - focused on supporting awareness raising programs. Amid this significant investment by multiple donors, it is hard to measure the exact impact of OSA has had through training and awareness raising. However, I’ve seen dramatic improvements in girls’ access to education, progress in the participation of women and girls in democratic practice and an increase in women’s access to justice and a reduction in negative traditional practices, which could be a result of NGO-led trainings supported by OSA and other donors.

However, based on my assessment I learned that trainings and awareness raising programs need to be very strategic, with professional trainers, and have a productive follow up which was often missed by OSA in the beginning of OSA’s activities in Afghanistan. Secondly, I concluded that it would be much better to pick one specific issue with a long-term strategic approach which would help us to measure the changes.  Fortunately based on the OSA’s new strategy and its objectives I believe that it will be easier to measure the impact of our work after a period of time.

I have also been reflecting on the extent to which “NGO-ization” has negatively impacted women’s rights work (which OSA has been part of).  By NGO-ization we mean the rapid growth of NGOs in Afghanistan - literally thousands of NGOs been registered over the past decade. The law concerning social organizations does not allow them to receive grants from the international donors, so only NGOs have had access to these resources, so they now dominate civil society. Most of these NGOs have focused on chasing project money, thus encouraging short term interventions, a donor-driven agenda, socially rootless presence, project duplication and the marginalization of under-represented civil society elements. In the case of women’s rights, some would argue that this encouraged a focus on the concerns of relatively urban women.

It also favors urban groups with English language skills, rather than smaller rural organizations, which would find it more challenging to meet the demands of international donors, including OSA. Even our English speaking urban groups complain that our systems are too English focused and time consuming for their capacities. OSA has attempted to introduce some diversity and regional programming, but realistically as a small organization our reach is limited.

Some women’s NGOs (and OSA) have tried to respond to this a range of actions, including strengthening NGO capacity and creating governmental and nongovernment common platforms such as the Afghan Women’s Network and the Ministry for Women’s Affairs, both of which can have a more strategic vision. However, many women’s social organizations, including universities and trade unions (nurses, teachers, and so on) are still marginalized, which is a factor that limits the base of women’s rights interventions.

Furthermore, I found that although there were very strong women’s organizations, coherence and long term follow up was still limited, in part a reflection of the enormous challenges facing women. This gap has been identified very clearly by most of women’s rights activists. Therefore, women’s rights activists have begun new initiatives to explore how to create long term movements that protect women’s rights (e.g. the Women Visioning Plan for 2014-2024).

The Way Forward

Based on our experience and lessons learned, we will establish a network of religious scholars in the region to promote and protect women’s rights advocates, particularly within the legal and political debate.  This initiative will be implemented with the coordination of a group of women’s rights activists who recently have started their advocacy and technical efforts in this regard. In a similar vein, we will provide scholarship opportunities for women’s rights advocates who want to become scholars and religious researchers.

OSA has strongly encouraged NGO grantees to broaden their activities in order to reach to the universities, unions, and other social movements. Modern Organization for Development of Education, Women and Children Legal Research Foundation and Feker Psychology and Research Organization are among the partners who have reached out to the universities to sensitize, build awareness, and mobilize students, particularly on EVAW. This could include national conferences and the introduction of an anti-sexual harassment coordination committee.

OSA also supports its partner NGOs to recognize the need to build constituencies over the long term, beyond their own individual organizations. The aim would be to broaden dialogue on equality and women rights during the transition period, instead of a one way intra-NGOs communication or monologue.

In our 2015 work plan we will add research to provide an updated view of women’s movements in Afghanistan, which can differentiate between NGOs and civil society in post-political transition, and provide examples of successful mobilization elsewhere, particularly by groups that have often been neglected in the discourse on social movements and civil society. This knowledge we will use to help women’s rights activists and organizations have a deeper analysis of the different strategies that civil society organizations and groups can use.

We expect there to be more opportunities to cooperate with other OSF programs and with the women’s rights program, including support for regional and international networking.

Given this fast changing situation, we will continually monitor the national climate on women’s rights in this time of uncertainty. With the election of Afghanistan’s first new president since 2001, the withdrawal of international forces, and the reduction of foreign assistance, much within the national political climate and economy will change. The impact of a significant drop in aid money to Afghanistan will have an impact on all of Afghan civil society, not least the women’s rights movement.

Most relevant new grantees (see annexe for more detail on grantees)

Empowerment Center for Women (ECW):  Is a women-led NGO, established in 1997, with a mission to improve the capabilities of Afghan women to participate in, negotiate with, influence, and hold accountable institutions that affect their lives. They have been approved as an eligible grantee. OSA has given them a grant for work on “Defending women’s Rights from Islamic Perspective”. ECW has experience of working with women’s rights and Sharia Law, they have staff with considerable expertise and recognition in Sharia, including Sharia experts in their Kabul and Kunduz offices.

The Feminine Solidarity for Justice Organization (FSJO): Is a civil society organization established in 2007, dedicated to empowering female victims of conflict. They seek an Afghan based solution to violence against women in Afghanistan, through community mobilization, awareness-building through workshops and media, advocacy and lobbying. FSJO takes the issue of sexual harassment of women and girls in work place serious with serious consequences for the perpetrator/s.

Women and Children Legal Research Foundation (WCLRF): Was established in Kabul in 2003 with two main components, research and advocacy and community empowerment. Recently they opened two small provincial offices in Balkh and Nengarhar. The overall purpose of WCLRF’s program is to empower women & children to claim their human rights, particularly their rights to dignity, equality and justice. WCLRF strives to make the voices of women and children heard in all regions of the country, encouraging men to accept the challenge of making communities and homes safe for women and children.

Feker Psychology and Research Organization (FPRO): Is an innovative organization whose primary mission is to address the mental, social, and cultural trauma of Afghan society and, through the application of behavioural sciences, to improve the general mental health of Afghan society. FPRO places a particular emphasis on providing psychological support for at-risk women and empowering them to advocate against gender discrimination.

Modern Organization for Development of Education (MODE): Is registered in 2009, formed by a group of young Afghan women in 2006 to promote women’s rights and education, through advocacy, capacity building and building human rights awareness. Mode has been nominated for the executive fund by OSA to receive support for organizational development.

Independent Election Commission ( IEC)