## Data & Conversion
Members & Dues | CAT-MOC to Member Credit check | x
Members & Dues | Contact Dump
Members & Dues | Dues Reporting | x
Admin & Reporting | Bridge Touchups
Admin & Reporting | Process Map for Imports
Admin & Reporting | Process Map for FEC reports
Admin & Reporting | User's Guides
PAC Fundraising | Contact Conversion
PAC Fundraising | PAC Callsheet (w/ giving history) | o
PAC Fundraising | PAC Industry Codes

## Developer Tasks
Subject | New | _Complete | Notes | Priority
Batch opening security
Finance Export/Report has incorrect totals for year/cycle | 1 | 0
Milly's Contrib By Batch | 0
Navision Export needs "07" pulled off of source codes
Negative total batches don't close | 0
Deposit Slip dates should not be NOW() | 0
ActBlue contribution type | 0
Notes field to appear on transmittal | 0
YTD totals not reflecting disbursements ??? | 0
Change CN to take notes on NULL links
Bringing Extra emails in from IMIS | 0 | 1 | Seperated Emails in IMIS imported into NGP | Complete
Tally Members Interface | 0 | 1 | Front-End Interface For Tally Code Control is broken | Complete
Deceased/DoNotMail | 0 | 1 | Moving Deceased/Do Not Mail Info From IMIS | Complete
Add Attribution | 0 | 1 | Adding Attribution to Contribution Page | Complete
Transmittal Forms | 0 | 1 | Finalize Transmittal Forms | Complete
Conduit Reporting | 0 | 1 |  | Complete
Fix Attribution | 1 | 1 | 2nd Attribution shows a very limited number of members…. | Complete
Show Donor on Conduit Disbursements | 0 | 1 | FEC report Information about disbursements from IMIS appears not to have been brought into NGP | Complete
Train DCCC on Entering Conduits | 1 | 1 | DCCC needs to be trained on entering Conduit Contributions | Complete
Tally Code Archive Suppression | 1 | 1 | Incorrect Tally Codes in Tally-Member Dropdown leave vast room for user-error. We need them filtered out. Talking to Eric tomorrow about that. | Complete
Train/Explain DCCC on Best-Efforts Letter Scheme | 1 | 1 | Review | Complete
Check FEC Report Match | 0 | 1 | Check the parallel FEC report & compare it to the one from IMIS | Complete
Conduit Transmittal doesn't show up | 0 | 1 | It errors out
Name to number on transmittals | 1 | 1 | Just change the name to the number | Normal
Error in Mail Merge | 1 | 1 | Fixed
Conduit Memo Transmittal Button doesn't post | 1 | 0
Shut Down Welcome Page | 0 | 0 | Welcome Page' displays sensitive information ; would prefer to have that function removed | Normal
Deposit Slips | 0 | 1 | Finish Deposit Slip Export for Jackie, Test with BOA | Critical
Conduit question re: status & accounting import | 1 | 1
Navision Bridge Export | 0 | 0 | Finish testing the "Navision Bridge Export" to our accounting system | Critical
Line 12 & 17 on FEC Report | 0 | 1 | Functionality for displaying Notes on Line 12 & 17 in FEC export (Unlimited Xfer) | Normal
Cash accounts are all 101 | 1
NTs should report on FEC report regardless | 1
Navision Exporet is limited by current recordset
Batch totals incorrect for partnerships
IMIS - NGP Comparison | 1